## WBS Dictionary
Risk Register
| CONTOSO CONSULTING | PROJECT ID | COMPANY | PROJECT MANAGER
| Contoso Consulting – Windows 11 Upgrade | CONT-11 | CONTOSO CONSULTING | Sana Rehman
TASK ID | TASK DESCRIPTION | Potential Risks and Mitigating Actions |  |  | Probability | Impact | Risk
1 | Project Management
1.1 | Develop project charter
1.1.1 | Define goals and objectives | Misalignment between project goals and business needs. Mitigation: Conduct stakeholder interviews to ensure clarity. |  |  | Medium | High | High
1.1.2 | Identify business drivers | Incomplete or outdated business drivers may lead to ineffective planning. Mitigation: Validate drivers with senior management. |  |  | low | medium | medium
1.2 | Identify stakeholders
1.2.1 | Executive stakeholders | Missed stakeholders can lead to lack of executive support. Mitigation: Use organizational chart and conduct stakeholder mapping. |  |  | medium | high | high
1.2.2 | Departmental leads | Incorrect or incomplete department contacts. Mitigation: Cross-check with HR and department heads. |  |  | medium | medium | medium
1.3 | Define project scope
1.3.1 | In-scope items | Scope creep due to poorly defined boundaries. Mitigation: Document scope clearly and get formal sign-off. |  |  | medium | medium | high
1.3.2 | Out-of-scope items | Unclear exclusions may result in misunderstandings. Mitigation: Clearly communicate what is not part of the project. |  |  | medium | high | medium
1.4 | Create project schedule
1.4.1 | Define milestones | Unrealistic or missed milestones affect project pacing. Mitigation: Set SMART milestones and review feasibility with teams. |  |  | medium | high | high
1.4.2 | Establish deadlines | Overly aggressive deadlines can lead to burnout. Mitigation: Build realistic timelines with buffer periods. |  |  | high | medium | high
1.5 | Manage project budget
1.5.1 | Track hardware costs | Untracked expenses may lead to budget overruns. Mitigation: Use centralized budget tracking tools and monitor weekly. |  |  | medium | high | high
1.5.2 | Monitor labor costs | Hidden overtime or staffing gaps can inflate costs. Mitigation: Monitor work hours and allocate resources efficiently. |  |  | low | medium | medium
1.6 | Monitor and report progress
1.6.1 | Weekly reports | Delayed reports may result in uninformed decisions. Mitigation: Automate status updates and assign reporting responsibility. |  |  | medium | medium | medium
1.6.2 | Stakeholder updates | Poor communication may cause stakeholder dissatisfaction. Mitigation: Use structured communication plan and feedback loops. |  |  | medium | high | high
1.7 | Final sign-off and closeout
1.7.1 | Review deliverables | Deliverables may not meet quality standards. Mitigation: Conduct peer reviews and use predefined quality metrics. |  |  | medium | mdeium | mdeium
1.7.2 | Final approval | Delays in sign-off may postpone project closure. Mitigation: Schedule review meetings early and follow up consistently. |  |  | low | medium | mdeium
2 | Inventory and Compatibility Assessment
2.1 | Gather hardware inventory from all offices
2.1.1 | Regional inventory collection | Incomplete or inconsistent data from offices. Mitigation: Assign clear responsibilities and use standardized templates. |  |  | high | high | high
2.1.2 | Centralized database update | Errors during data consolidation or missed updates. Mitigation: Implement data validation rules and regular backups. |  |  | medium | high | high
2.2 | Centralized database update
2.2.1 | CPU and TPM validation | Misidentification of incompatible hardware. Mitigation: Use automated scanning tools and double-check edge cases |  |  | medium | medium | medium
2.2.2 | Memory and disk check | Inaccurate or outdated hardware specs may affect results. Mitigation: Schedule real-time checks and use verified tools. |  |  | medium | medium | medium
2.3 | Identify systems for upgrade vs. replacement
2.3.1 | Create replacement list | Critical devices may be incorrectly flagged. Mitigation: Review results with local IT teams before finalizing. |  |  | medium | high | high
2.3.2 | Identify upgrade-ready systems | Missed upgrade candidates may result in unnecessary purchases. Mitigation: Cross-check upgrade potential with manufacturers. |  |  | low | medium | medium
2.4 | Document compatibility results
2.4.1 | Generate reports by region | Regional IT may not follow reporting format. Mitigation: Provide templates and training sessions beforehand. |  |  | medium | medium
2.4.2 | Submit to management | Delayed submissions can affect procurement and scheduling. Mitigation: Set hard deadlines and use reminders. |  |  | medium | high | high
2.5 | Submit assessment report
2.5.1 | Compile data | Data corruption or loss during compilation. Mitigation: Use secure shared storage and version control. |  |  | low | high | medium
2.5.2 | Final review and submission | Oversights during review may lead to faulty decisions. Mitigation: Assign dual reviewers and use checklists. |  |  | medium | medium | medium
3 | Procurement and Licensing
3.1 | Define hardware specifications
3.1.1 | Desktop specs | Specs may not meet future software requirements. Mitigation: Consult software teams and future-proof hardware. |  |  | medium | high | high
3.1.2 | Laptop specs | Portability vs. performance trade-offs may be misjudged. Mitigation: Create user-based device profiles and test models. |  |  | medium | medium | medium
3.2 | Select and approve vendors
3.2.1 | Solicit quotes | Vendors may delay responses or provide incomplete quotes. Mitigation: Engage multiple vendors and set strict RFQ deadlines. |  |  | high | medium | high
3.2.2 | Evaluate proposals | Biased evaluation or overlooking key factors. Mitigation: Use a weighted scoring system and include cross-functional reviewers. |  |  | medium | medium | medium
3.3 | Purchase 1,200 new Windows 11-compatible systems
3.3.1 | Issue purchase orders | Delays in PO processing may delay deployment. Mitigation: Pre-approve purchase requisitions and streamline approval chain. |  |  | high | high | high
3.3.2 | Confirm delivery schedule | Supply chain disruptions or vendor overpromising. Mitigation: Set contractual delivery clauses and maintain vendor backup list. |  |  | medium | high | high
3.4 | Acquire Microsoft Volume Licensing
3.4.1 | Validate licensing needs | Under/overestimation can lead to compliance issues or overspending. Mitigation: Audit existing licenses and forecast future needs. |  |  | medium | high | high
3.4.2 | Finalize agreement | Delays due to legal review or negotiation conflicts. Mitigation: Engage legal early and define clear licensing scope. |  |  | medium | high | medium
3.5 | Receive and verify shipments
3.5.1 | Inspect hardware | Received items may be damaged or incorrect. Mitigation: Perform spot-checks and document all inspections. |  |  | medium | high | high
3.5.2 | Update asset inventory | Items may be missed or misrecorded. Mitigation: Use barcode scanning and dual verification process. |  |  | low | high | medium
4 | Deployment Planning
4.1 | Develop deployment strategy and schedule
4.1.1 | Create regional rollout plan | Poor coordination may disrupt operations. Mitigation: Align rollout with business calendars and get regional input. |  |  | medium | high | high
4.1.2 | Align with business priorities | Misalignment could impact critical departments. Mitigation: Involve department leads during planning phase. |  |  | medium | medium | medium
4.2 | Assign regional IT leads
4.2.1 | Confirm availability | Regional leads may have other commitments. Mitigation: Secure formal commitment and back-up resources. |  |  | low | medium | medium
4.2.2 | Define responsibilities | Ambiguities can lead to task overlaps or gaps. Mitigation: Clearly document RACI roles and responsibilities. |  |  | medium | high | medium
4.3 | Prepare imaging and configuration tools
4.3.1 | Build standard OS image | Incompatibilities with hardware or software. Mitigation: Test across hardware models and include IT support feedback. |  |  | medium | high | medium
4.3.2 | Test configuration settings | Missed configuration errors can cause deployment failures. Mitigation: Run test deployments in sandbox environments. |  |  | medium | high | high
4.4 | Set up centralized deployment tools (MECM/WDS)
4.4.1 | Install and configure servers | Server setup may face delays or misconfiguration. Mitigation: Use validated installation checklists and assign experienced staff. |  |  | medium | high | high
4.4.2 | Validate deployment pipeline | Errors in automation scripts or software integration. Mitigation: Conduct dry runs and validate logs before full rollout. |  |  | medium | medium | medium
4.5 | Prepare backup and recovery solutions
4.5.1 | Select tools and methods | Inadequate backup tools may risk data loss. Mitigation: Choose tested, enterprise-grade backup solutions. |  |  | low | high | medium
4.5.2 | Test restore process | Incomplete or slow restoration processes. Mitigation: Perform trial restores for different user profiles and document results. |  |  | medium | high | high
5 | System Deployment and Migration
5.1 | Backup user data and profiles
5.1.1. | Automate backup scripts | Scripts may fail or miss user data. Mitigation: Test scripts extensively and schedule regular backups before deployment. |  |  | medium | high | high
5.1.2 | Store data securely | Backup data could be lost or accessed without authorization. Mitigation: Use encrypted storage and access controls. |  |  | medium | medium | high
5.2 | Deploy Windows 11 on compatible systems
5.2.1 | Schedule upgrade | Poor scheduling may impact user productivity. Mitigation: Coordinate with departments and schedule outside peak hours |  |  | medium | mmedium | medium
6.2.2. | Monitor for issues | Unnoticed failures may escalate. Mitigation: Assign dedicated monitoring personnel and create real-time alerts. |  |  | high | medium | high
5.3 | Replace legacy systems with new hardware
5.3.1 | Set up new devices | Hardware issues or incorrect configurations. Mitigation: Follow standard deployment procedures and QA checklist. |  |  | medium | medium | medium
5.3.2 | Transfer user roles | Incorrect role assignment can cause access issues. Mitigation: Validate roles through user confirmations post-migration. |  |  | medium | hugh | high
5.4 | Restore user data and profiles
5.4.1 | Run restore utility | Restore may fail or be incomplete. Mitigation: Conduct test restores and maintain backup integrity checks. |  |  | medium | high | high
5.4.2 | Verify user access | Missed permissions may hinder user tasks. Mitigation: Confirm access through post-deployment testing. |  |  | medium | medium | medium
5.5 | Verify system functionality and network access
5.5.1 | Test software and connections | Applications may not function correctly on new systems. Mitigation: Pre-test core apps and network connectivity in test group. |  |  | medium | high | hugh
5.5.2 | Confirm user satisfaction | Lack of feedback may hide issues. Mitigation: Use structured surveys and quick feedback loops post-deployment. |  |  | low | medium | medium
6 | User Training and Documentation
6.1 | Develop training materials and user guides
6.1.1 | Create multilingual content | Translations may be inaccurate or delayed. Mitigation: Use professional translation services and validate with native speakers |  |  | medium | medium | medium
6.1.2 | Develop role-based guides | Incomplete or unclear instructions for certain roles. Mitigation: Involve end-users from each role in review and feedback. |  |  | medium | medium | medium
6.2 | Schedule training sessions
6.2.1 | Coordinate with departments | Scheduling conflicts may lead to poor attendance. Mitigation: Plan sessions well in advance and offer multiple time slots. |  |  | low | medium | medium
6.2.2 | Send invites and materials | Missed communications or outdated content. Mitigation: Use centralized communication tools and double-check content updates. |  |  | medium | medium | medium
6.3 | Deliver live or virtual training sessions
6.3.1 | Conduct instructor-led sessions | Technical issues or lack of engagement. Mitigation: Test virtual tools beforehand and make sessions interactive. |  |  | medium | medium | medium
6.3.2 | Provide self-paced modules | Low completion rates. Mitigation: Track participation and send reminders; include completion incentives. |  |  | medium | low | medium
6.4 | Provide multilingual support (EN, FR, SP, MAN)
6.4.1 | Translate documents | Inaccurate or inconsistent terminology. Mitigation: Standardize terminology and use a central glossary for all translations. |  |  | medium | low | medium
6.4.2 | Staff language-specific support | Insufficient staff for non-English speakers. Mitigation: Identify needs early and assign dedicated multilingual support. |  |  | medium | medium | high
6.5 | Distribute documentation and FAQs
6.5.1 | Email digital copies | Emails may go to spam or be missed. Mitigation: Use internal notification systems in addition to email. |  |  | low | low | low
6.5.2 | Upload to company portal | Portal access issues or outdated uploads. Mitigation: Test portal availability and designate a portal content manager. |  |  | low | medium | medium
7 | Testing and Support
7.1 | Conduct User Acceptance Testing (UAT)
7.1.1 | Define test cases | Incomplete coverage of scenarios. Mitigation: Involve cross-functional teams in test case creation and perform peer reviews. |  |  | medium | high | high
7.1.2 | Collect test results | Inconsistent or inaccurate test data. Mitigation: Use standardized templates and assign data collection responsibilities. |  |  | medium | medium | medium
7.2 | Collect feedback and resolve post-deployment issues
7.2.1 | Open feedback channels | Feedback tools may be underutilized. Mitigation: Promote feedback options and train users on how to use them. |  |  | medium | nedium | medium
7.2.2 | Track and resolve tickets | High ticket volume may delay resolutions. Mitigation: Prioritize by severity and increase support staff during rollout. |  |  | high | high | high
7.3 | Monitor system performance
7.3.1 | Track KPIs | Key performance indicators may be undefined or misaligned. Mitigation: Define KPIs clearly during planning and monitor continuously. |  |  | medium | medium | medium
7.3.2 | Log incidents | Incidents may not be reported consistently. Mitigation: Implement an easy-to-use incident reporting system with clear guidelines. |  |  | medium | medium | medium
7.4 | Provide IT helpdesk and on-site support
7.4.1 | Staff helpdesk | Insufficient helpdesk coverage. Mitigation: Schedule shifts carefully and assign backup personnel for peak times |  |  | high | high | high
7.4.2 | Schedule onsite assistance | Availability conflicts or travel delays. Mitigation: Coordinate schedules early and have regional backups in place. |  |  | medium | medium | medium
7.5 | Final system verification
7.5.1 | Conduct walkthroughs | Missed errors during walkthroughs. Mitigation: Use standardized checklists and ensure team participation. |  |  | medium | medium | medium
7.5.2 | Confirm readiness with users | Lack of user engagement or delayed feedback. Mitigation: Follow up directly with key users and collect formal confirmations. |  |  | medium | medium | medium
8 | Decommissioning and Recycling
8.1 | Collect and inventory old systems
8.1.1 | Tag devices | Devices may be missed or mislabelled. Mitigation: Use barcode scanners and maintain a checklist for each site. |  |  | medium | medium | medium
8.1.2 | Record serial numbers | Manual entry errors or incomplete logs. Mitigation: Use automated tools and perform double-checks. |  |  | medium | medium | medium
8.2 | Wipe data securely
8.2.1 | Use certified tools | Use of unapproved or outdated wiping tools. Mitigation: Validate tool certification and ensure latest versions are installed. |  |  | low | high | medium
8.2.2 | Document data erasure | Missing or non-compliant audit records. Mitigation: Automate logging and maintain centralized documentation. |  |  | medium | high | high
8.3 | Recycle or dispose of hardware per policy
8.3.1 | Work with recycling vendor | Vendor delays or non-compliance. Mitigation: Vet vendors thoroughly and include service-level agreements in contracts. |  |  | low | medium | high
8.3.2 | Provide proof of disposal | Incomplete or lost documentation. Mitigation: Require digital receipts and confirmations from vendors. |  |  | medium | medium | medium
8.4 | Update asset management records
8.4.1 | Remove decommissioned devices | Devices remain active in asset system. Mitigation: Sync asset management updates with decommissioning schedule. |  |  | medium | medium | medium
8.4.2 | Update lifecycle status | Lifecycle status not updated properly. Mitigation: Assign responsibility and verify updates post-process. |  |  | low | medium | medium
9 | Project Closure
9.1 | Final review and evaluation
9.1.1 | Conduct performance review | Incomplete or biased evaluations. Mitigation: Include diverse stakeholders and use structured review templates. |  |  | medium | medium | medium
9.1.2 | Identify success criteria met | Lack of clarity on goals or criteria. Mitigation: Refer to the original project charter and validate against metrics. |  |  | medium | medium | medium
9.2 | Obtain sign-off from stakeholders
9.2.1 | Schedule final presentation | Key stakeholders may be unavailable. Mitigation: Plan well in advance and offer multiple session options. |  |  | low | medium | medium
9.2.2 | Get written approval | Delays in sign-off. Mitigation: Send reminders and follow up with stakeholders proactively. |  |  | medium | high | high
9.3 | Archive documentation and reports
9.3.1 | Save project files securely | Files may be lost or misfiled. Mitigation: Use version-controlled, cloud-based storage with backups. |  |  | low | high | medium
9.3.2' | Notify IT and management | Miscommunication may delay transition. Mitigation: Send formal closure memo and follow up for acknowledgment. |  |  | low | medium | medium
9.4 | Conduct lessons learned session
9.4.1 | Host debrief meeting | Low attendance or engagement. Mitigation: Make it interactive, short, and focused on improvement. |  |  | medium | low | medium
9.4.2 | Compile lessons learned document | Incomplete or overly generic content. Mitigation: Assign experienced facilitator to collect feedback and summarize insights. |  |  | medium | medium | medium
0
0
0
0
0
0
0
0
0
0
0
0
0
[5 empty] | 5 | 4 | 20
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[5 empty] | 2 | 7 | 14
0
0
[5 empty] | 2 | 8 | 16
[5 empty] | 1 | 6 | 6
[5 empty] | 7 | 7 | 49
0
[5 empty] | 4 | 4 | 16
[5 empty] | 2 | 6 | 12

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.