## Project schedule
| Contoso Conslting Windows 11 upgrade | [5 empty] | Project start: | [7 empty] | 2025-04-07
| Project ID : CONT-11 | Project manager: Sana Rehman |  |  |  |  | Display week: | [7 empty] | 1
Company: Contoso Consulting
[7 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26
TASK ID | TASK | ASSIGNED TO | PROGRESS | START | END | DURATION | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
1 | Project Management
1.1 | Develop project charter | Sana | 97% | 2025-04-07 | 2025-04-09 | 3 | bar: M to W
1.1.1 | Define goals and objectives | Sana | 99% | 2025-04-07 | 2025-04-07 | 1
1.1.2 | Identify business drivers | Sana | 94% | 2025-04-07 | 2025-04-08 | 2
1.2 | Identify stakeholders | Sana | 98% | 2025-04-09 | 2025-04-10 | 2
1.2.1 | Executive stakeholders | Sana | 99% | 2025-04-09 | 2025-04-09 | 1
1.2.2 | Departmental leads | Sana | 100% | 2025-04-10 | 2025-04-10 | 1
1.3 | Define project scope | Sana | 100% | 2025-04-11 | 2025-04-14 | 4
1.3.1 | In-scope items | Sana | 50% | 2025-04-11 | 2025-04-12 | 2
1.3.2 | Out-of-scope items | Sana | 50% | 2025-04-12 | 2025-04-14 | 3
1.4 | Create project schedule | Sana | 50% | 2025-04-15 | 2025-04-18 | 4
1.4.1 | Define milestones | Sana | 50% | 2025-04-15 | 2025-04-16 | 2
1.4.2 | Establish deadlines | Sana | 50% | 2025-04-16 | 2025-04-17 | 2
1.5 | Manage project budget | Zain | 0% | 2025-04-19 | 2025-04-22 | 4
1.5.1 | Track hardware costs | Zain | 0% | 2025-04-19 | 2025-04-20 | 2
1.5.2 | Monitor labor costs | Zain | 0% | 2025-04-20 | 2025-04-21 | 2
1.6 | Monitor and report progress | Sana | 0% | 2025-04-23 | 2025-04-26 | 4
1.6.1 | Weekly reports | Sana | 17.62% | 2025-04-23 | 2025-04-23 | 1
1.6.2 | Stakeholder updates | Sana | 0% | 2025-04-24 | 2025-04-25 | 2
1.7 | Final sign-off and closeout | Sana | 0% | 2025-04-27 | 2025-05-01 | 5
1.7.1 | Review deliverables | Sana | 0% | 2025-04-27 | 2025-04-28 | 2
1.7.2 | Final approval | Sana | 0% | 2025-04-28 | 2025-04-29 | 2
2 | Inventory and Compatibility Assessment
2.1 | Gather hardware inventory from all offices | Alia | 60% | 2025-04-07 | 2025-04-10 | 4
2.1.1 | Regional inventory collection | Alia | 100% | 2025-04-07 | 2025-04-08 | 2
2.1.2 | Centralized database update | Alia | 100% | 2025-04-08 | 2025-04-09 | 2
2.2 | Centralized database update | CHEN | 50% | 2025-04-09 | 2025-04-11 | 3
2.2.1 | CPU and TPM validation | CHEN | 60% | 2025-04-09 | 2025-04-10 | 2
2.2.2 | Memory and disk check | CHEN | 0% | 2025-04-10 | 2025-04-11 | 2
2.3 | Identify systems for upgrade vs. replacement | Lisa | 0% | 2025-04-11 | 2025-04-13 | 3
2.3.1 | Create replacement list | Lisa | 0% | 2025-04-11 | 2025-04-12 | 2
2.3.2 | Identify upgrade-ready systems | Lisa | 0% | 2025-04-12 | 2025-04-13 | 2
2.4 | Document compatibility results | Alia | 0% | 2025-04-13 | 2025-04-14 | 2
2.4.1 | Generate reports by region | Alia | 0% | 2025-04-13 | 2025-04-14 | 2
2.4.2 | Submit to management | Alia | 0% | 2025-04-14 | 2025-04-14 | 1
2.5 | Submit assessment report | Alia | 0% | 2025-04-14 | 2025-04-15 | 2
2.5.1 | Compile data | Alia | 0% | 2025-04-14 | 2025-04-15 | 2
2.5.2 | Final review and submission | Sana | 0% | 2025-04-15 | 2025-04-15 | 1
3 | Procurement and Licensing
3.1 | Define hardware specifications | Lisa | 0% | 2025-04-16 | 2025-04-17 | 2
3.1.1 | Desktop specs | Lisa | 0% | 2025-04-16 | 2025-04-16 | 1
3.1.2 | Laptop specs | Lisa | 0% | 2025-04-16 | 2025-04-17 | 2
3.2 | Select and approve vendors | Fatima | 0% | 2025-04-17 | 2025-04-19 | 3
3.2.1 | Solicit quotes | Fatima | 0% | 2025-04-17 | 2025-04-18 | 2
3.2.2 | Evaluate proposals | Fatima | 0% | 2025-04-18 | 2025-04-19 | 2
3.3 | Purchase 1,200 new Windows 11-compatible systems | Fatima | 0% | 2025-04-20 | 2025-04-22 | 3
3.3.1 | Issue purchase orders | Fatima | 0% | 2025-04-20 | 2025-04-21 | 2
3.3.2 | Confirm delivery schedule | Fatima | 0% | 2025-04-21 | 2025-04-22 | 2
3.4 | Acquire Microsoft Volume Licensing | Amir | 0% | 2025-04-22 | 2025-04-25 | 4
3.4.1 | Validate licensing needs | Amir | 0% | 2025-04-22 | 2025-04-23 | 2
3.4.2 | Finalize agreement | Amir | 0% | 2025-04-24 | 2025-04-25 | 2
3.5 | Receive and verify shipments | Alia | 0% | 2025-04-24 | 2025-05-01 | 8
3.5.1 | Inspect hardware | Alia | 0% | 2025-04-26 | 2025-04-30 | 5
3.5.2 | Update asset inventory | Alia | 0% | 2025-05-01 | 2025-05-01 | 1
4 | Deployment Planning
4.1 | Develop deployment strategy and schedule | Irfan | 0% | 2025-05-02 | 2025-05-04 | 3
4.1.1 | Create regional rollout plan | Irfan | 0% | 2025-05-02 | 2025-05-03 | 2
4.1.2 | Align with business priorities | Irfan | 0% | 2025-05-03 | 2025-05-04 | 2
4.2 | Assign regional IT leads | Sana | 0% | 2025-05-05 | 2025-05-06 | 2
4.2.1 | Confirm availability | Sana | 0% | 2025-05-05 | 2025-05-05 | 1
4.2.2 | Define responsibilities | Sana | 0% | 2025-05-06 | 2025-05-06 | 1
4.3 | Prepare imaging and configuration tools | Chen | 0% | 2025-05-07 | 2025-05-10 | 4
4.3.1 | Build standard OS image | Chen | 0% | 2025-05-07 | 2025-05-08 | 2
4.3.2 | Test configuration settings | Chen | 0% | 2025-05-09 | 2025-05-10 | 2
4.4 | Set up centralized deployment tools (MECM/WDS) | Chen | 0% | 2025-05-11 | 2025-05-15 | 5
4.4.1 | Install and configure servers | Chen | 0% | 2025-05-11 | 2025-05-13 | 3
4.4.2 | Validate deployment pipeline | Chen | 0% | 2025-05-14 | 2025-05-15 | 2
4.5 | Prepare backup and recovery solutions | Lisa | 0% | 2025-05-16 | 2025-05-18 | 3
4.5.1 | Select tools and methods | Lisa | 5.571% | 2025-05-16 | 2025-05-17 | 2
4.5.2 | Test restore process | Lisa | 0% | 2025-05-17 | 2025-05-18 | 2
5 | System Deployment and Migration
5.1 | Backup user data and profiles | Emma | 70% | 2025-04-18 | 2025-04-22 | 5
5.1.1. | Automate backup scripts | Emma | 100% | 2025-04-15 | 2025-04-16 | 2
5.1.2 | Store data securely | Emma | 60% | 2025-04-17 | 2025-04-19 | 3
5.2 | Deploy Windows 11 on compatible systems | Andre | 0% | 2025-04-23 | 2025-04-30 | 8
5.2.1 | Schedule upgrade | Andre | 0% | 2025-04-21 | 2025-04-22 | 2
6.2.2. | Monitor for issues | Andre | 0% | 2025-04-23 | 2025-05-01 | 9
5.3 | Replace legacy systems with new hardware | Mei | 0% | 2025-05-02 | 2025-05-10 | 9
5.3.1 | Set up new devices | Mei | 0% | 2025-05-03 | 2025-05-07 | 5
5.3.2 | Transfer user roles | Mei | 0% | 2025-05-08 | 2025-05-09 | 2
5.4 | Restore user data and profiles | Mei | 0% | 2025-05-11 | 2025-05-14 | 4
5.4.1 | Run restore utility | David | 0% | 2025-05-11 | 2025-05-12 | 2
5.4.2 | Verify user access | David | 0% | 2025-05-13 | 2025-05-14 | 2
5.5 | Verify system functionality and network access | Andre | 0% | 2025-05-15 | 2025-05-18 | 4
5.5.1 | Test software and connections | Andre | 0% | 2025-05-15 | 2025-05-16 | 2
5.5.2 | Confirm user satisfaction | Andre | 0% | 2025-05-17 | 2025-05-18 | 2
6 | User Training and Documentation
6.1 | Develop training materials and user guides | Ravi | 40% | 2025-04-18 | 2025-04-25 | 8
6.1.1 | Create multilingual content | Ravi | 0% | 2025-04-19 | 2025-04-23 | 5
6.1.2 | Develop role-based guides | Ravi | 50% | 2025-04-18 | 2025-04-24 | 7
6.2 | Schedule training sessions | Ravi | 0% | 2025-04-25 | 2025-04-27 | 3
6.2.1. | Coordinate with departments | Ravi | 0% | 2025-04-25 | 2025-04-26 | 2
6.2.2 | Send invites and materials | Ravi | 0% | 2025-04-26 | 2025-04-27 | 2
6.3 | Deliver live or virtual training sessions | Ravi | 0% | 2025-04-28 | 2025-05-02 | 5
6.3.1 | Conduct instructor-led sessions | Ravi | 0% | 2025-04-28 | 2025-04-30 | 3
6.3.2 | Provide self-paced modules | Ravi | 0% | 2025-04-29 | 2025-05-02 | 4
6.4 | Provide multilingual support (EN, FR, SP, MAN) | Ravi | 0% | 2025-05-01 | 2025-05-05 | 5
6.4.1 | Translate documents | Ravi | 70% | 2025-04-20 | 2025-04-23 | 4
6.4.2 | Staff language-specific support | Ravi | 0% | 2025-05-01 | 2025-05-05 | 5
6.5 | Distribute documentation and FAQs | Ravi | 0% | 2025-05-03 | 2025-05-04 | 2
6.5.1 | Email digital copies | Ravi | 0% | 2025-05-03 | 2025-05-03 | 1
6.5.2 | Upload to company portal | Ravi | 0% | 2025-05-03 | 2025-05-04 | 2
7 | Testing and Support
7.1 | Conduct User Acceptance Testing (UAT) | Ron | 0% | 2025-05-05 | 2025-05-09 | 5
7.1.1 | Define test cases | Ron | 0% | 2025-05-05 | 2025-05-06 | 2
7.1.2 | Collect test results | Ron | 0% | 2025-05-06 | 2025-05-09 | 4
7.2 | Collect feedback and resolve post-deployment issues | Aisha | 0% | 2025-05-10 | 2025-05-17 | 8
7.2.1 | Open feedback channels | Aisha | 0% | 2025-05-10 | 2025-05-11 | 2
7.2.2 | Track and resolve tickets | Aisha | 0% | 2025-05-11 | 2025-05-17 | 7
7.3 | Monitor system performance | Ron | 0% | 2025-05-10 | 2025-05-20 | 11
7.3.1 | Track KPIs | Ron | 0% | 2025-05-10 | 2025-05-15 | 6
7.3.2 | Log incidents | Ron | 0% | 2025-05-11 | 2025-05-20 | 10
7.4 | Provide IT helpdesk and on-site support | Aisha | 0% | 2025-05-01 | 2025-05-20 | 20
7.4.1 | Staff helpdesk | Aisha | 0% | 2025-05-01 | 2025-05-04 | 4
7.4.2 | Schedule onsite assistance | Aisha | 0% | 2025-05-03 | 2025-05-20 | 18
7.5 | Final system verification | Aisha | 0% | 2025-05-20 | 2025-05-22 | 3
7.5.1 | Conduct walkthroughs | Aisha | 0% | 2025-05-20 | 2025-05-21 | 2
7.5.2 | Confirm readiness with users | Aisha | 0% | 2025-05-21 | 2025-05-22 | 2
8 | Decommissioning and Recycling
8.1 | Collect and inventory old systems | Zara | 0% | 2025-05-28 | 2025-05-30 | 3
8.1.1 | Tag devices | Zara | 0% | 2025-05-28 | 2025-05-29 | 2
8.1.2 | Record serial numbers | Zara | 0% | 2025-05-29 | 2025-05-30 | 2
8.2 | Wipe data securely | Zara | 0% | 2025-05-31 | 2025-06-01 | 2
8.2.1 | Use certified tools | Zara | 0% | 2025-05-31 | 2025-05-31 | 1
8.2.2 | Document data erasure | Zara | 0% | 2025-06-01 | 2025-06-01 | 1
8.3 | Recycle or dispose of hardware per policy | Zara | 0% | 2025-06-02 | 2025-06-04 | 3
8.3.1 | Work with recycling vendor | Zara | 0% | 2025-06-02 | 2025-06-03 | 2
8.3.2 | Provide proof of disposal | Zara | 0% | 2025-06-04 | 2025-06-04 | 1
8.4 | Update asset management records | Alia | 0% | 2025-06-05 | 2025-06-06 | 2
8.4.1 | Remove decommissioned devices | Alia | 0% | 2025-06-05 | 2025-06-05 | 1
8.4.2 | Update lifecycle status | Alia | 0% | 2025-06-06 | 2025-06-06 | 1
9 | Project Closure
9.1 | Final review and evaluation | Sana | 0% | 2025-06-03 | 2025-06-04 | 2
9.1.1 | Conduct performance review | Sana | 0% | 2025-06-03 | 2025-06-03 | 1
9.1.2 | Identify success criteria met | Sana | 0% | 2025-06-04 | 2025-06-04 | 1
9.2 | Obtain sign-off from stakeholders | Sana | 0% | 2025-06-05 | 2025-06-05 | 1
9.2.1 | Schedule final presentation | Sana | 0% | 2025-06-05 | 2025-06-05 | 1
9.2.2 | Get written approval | Sana | 0% | 2025-06-05 | 2025-06-05 | 1
9.3 | Archive documentation and reports | Sana | 0% | 2025-06-05 | 2025-06-06 | 2
9.3.1 | Save project files securely | Sana | 0% | 2025-06-05 | 2025-06-05 | 1
9.3.2' | Notify IT and management | Sana | 0% | 2025-06-06 | 2025-06-06 | 1
9.4 | Conduct lessons learned session | Sana | 0% | 2025-06-06 | 2025-06-06 | 1
9,4,1 | Host debrief meeting | Sana | 0% | 2025-06-06 | 2025-06-06 | 1
9,4,2 | Compile lessons learned document | Sana | 0% | 2025-06-06 | 2025-06-06 | 1
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.