Contoso Consulting – Windows 11 Upgrade Project Charter

Project Title:
Contoso Consulting Windows 11 Upgrade

Project ID:
Cont-11

Executive Sponsor:
Jennifer Li, CIO – Contoso Consulting

Project Manager:
Sana Rehman

Date:
April 14, 2025

1. Project Purpose and Justification

The purpose of the Windows 11 Upgrade Project is to upgrade or replace all computers across Contoso Consulting’s global network to support Windows 11. This initiative is essential for launching a centralized enterprise software platform, improving operational efficiency, and aligning with ISO certification requirements. Upgrading ensures compliance with modern security standards, provides a streamlined user experience, and prepares the company for long-term technology support.

2. Project Objectives

- Assess all 3,200 existing systems for Windows 11 compatibility.

- Replace approximately 1,200 legacy systems that do not meet the Windows 11 requirements.

- Successfully deploy Windows 11 across all corporate and regional offices.

- Preserve user data and settings during migration.

- Provide comprehensive user training to reduce disruption.

- Complete the project within the two-month timeline and within the allocated budget.

3. Key Requirements

- Procurement of 1,200 new Windows 11-compatible desktops and laptops.

- Microsoft Volume Licensing for Windows 11 deployment.

- Centralized deployment tools (e.g., Microsoft Endpoint Configuration Manager, Windows Deployment Services).

- Backup and recovery tools for secure data migration.

- Regional IT leads and helpdesk staff to assist with deployment.

- Documentation team and training coordinators for end-user onboarding.

4. Scope

In Scope:

- Inventory and compatibility analysis.

- Procurement and deployment of new systems.

- Data backup, migration, and OS upgrade to Windows 11.

- Decommissioning and recycling of old hardware.

- User acceptance testing (UAT) and post-deployment support.

- User training and distribution of documentation.

Out of Scope:

- Server infrastructure upgrades.

- Changes to non-Windows operating systems or unrelated third-party applications.

5. High-Level Requirements

- All systems must meet Windows 11 hardware requirements.

- User data and profiles must be preserved.

- Network services must remain functional post-upgrade.

- Multilingual support: English, French, Spanish, and Mandarin.

- Compliance with IT security and corporate standards.

6. Deliverables and Milestones

| Milestone | Target Date |
| --- | --- |
| Project Kickoff | April 7, 2025 |
| Inventory and Compatibility Analysis Complete | April 14, 2025 |
| Procurement of New Systems | April 21, 2025 |
| Begin Deployment | April 28, 2025 |
| Complete Deployment | May 23, 2025 |
| User Training Completed | May 30, 2025 |
| Final Testing and Signoff | June 4, 2025 |
| Project Closeout | June 6, 2025 |

7. Budget Estimate

| Item | Estimated Cost (CAD) |
| --- | --- |
| Hardware Purchase | $960,000 |
| Licensing | $480,000 |
| Labour (internal/contractor) | $300,000 |
| Training & Support Materials | $60,000 |
| Contingency (10%) | $180,000 |
| Total Budget | $1,980,000 |

8. Project Risks

- Compatibility issues with legacy systems.

- Hardware delivery delays due to supply chain constraints.

- End-user resistance or delays in training participation.

- Possible downtime during transition.

- Risk of data loss during the migration process.

9. Assumptions and Constraints

Assumptions:

- Regional offices will cooperate with local IT support.

- Funding will be approved and released on time.

- Internet bandwidth will support remote deployments.

Constraints:

- Must be completed within Q2 2025.

- Budget cannot exceed $2 million CAD.

- Limited IT staffing in some regions.

10. Stakeholders

- Executive Sponsor: Jennifer Li, CIO – Contoso Consulting

- Project Manager: Sana Rehman

- Project Stakeholder: Alicia Menendez, VP of Operations – amenendez@contoso.com | Cell: 416.555.0099

- IT Department: Regional IT Leads

- End Users: All Contoso Consulting Staff

- Training Coordinators: HR and Learning & Development

- Vendors: Hardware suppliers, Microsoft Licensing Partners

11. Criteria for Success

The project will be deemed successful when:

- All systems have been upgraded to Windows 11.

- No critical data is lost during the migration.

- Deployment is verified and approved by regional IT teams.

- All users receive appropriate training and documentation.

- The CIO and project sponsor formally sign off on the completed project.

12. Approval

| Name | Title | Signature | Date |
| --- | --- | --- | --- |
| Jennifer Li | CIO, Contoso Consulting |  | April 7, 2025 |
| Sana Rehman | Project Manager |  | April 7, 2025 |