## WBS Dictionary
RAM (RACI) Chart
| PROJECT TITLE | PROJECT ID | COMPANY | PROJECT MANAGER
| Contoso Consulting – Windows 11 Upgrade | CONT-11 | Contoso Consulting | Sana Rehman
TASK ID | TASK DESCRIPTION | Sana | Irfan | Ron | Chen | Lisa | Alia | Fatima | Zain | Zara | Amin | Ravi | Aisha | Emma | Andre | Mei | David
1 | Project Management
1.1 | Develop project charter | A | C |  | R | R |  |  | C |  |  |  |  | C | C | C | C
1.1.1 | Define goals and objectives | A | C |  | R | R | [7 empty] | C | C | C | C
1.1.2 | Identify business drivers | R | C |  | R | R | [7 empty] | C | C | C | C
1.2 | Identify stakeholders | A | R |  | R | R | [7 empty] | C | C | C | C
1.2.1 | Executive stakeholders | A | C | [5 empty] | C |  |  |  |  | I | I | I | I
1.2.2 | Departmental leads | A | C | [10 empty] | R (Region Leads) | R (Region Leads) | R (Region Leads) | R (Region Leads)
1.3 | Define project scope | A | C |  | R | R | [7 empty] | C | C | C | C
1.3.1 | In-scope items | A | C |  | R | R | [7 empty] | C | C | C | C
1.3.2 | Out-of-scope items | A | C |  | R | R | [7 empty] | C | C | C | C
1.4 | Create project schedule | A | R |  | C | C | [7 empty] | C | C | C | C
1.4.1 | Define milestones | A | R |  | C | C | [7 empty] | C | C | C | C
1.4.2 | Establish deadlines | A | R |  | C | C | [7 empty] | C | C | C | C
1.5 | Manage project budget | A | C |  |  |  |  | C | C |  |  |  |  | I | I | I | I
1.5.1 | Track hardware costs | R | C |  |  |  | R | C | [5 empty] | I | I | I | I
1.5.2 | Monitor labor costs | A | C | [5 empty] | R |  |  |  |  | I | I | I | I
1.6 | Monitor and report progress | A | R |  | R | R | [6 empty] | R | C | C | C | C
1.6.1 | Weekly reports | A | R |  | R | R | [6 empty] | R | I | I | I | I
1.6.2 | Stakeholder updates | A | C |  | C | C | [6 empty] | C | R (Region Leads) | R (Region Leads) | R (Region Leads) | R (Region Leads)
1.7 | Final sign-off and closeout | A | R | [5 empty] | C |  |  |  |  | I | I | I | I
1.7.1 | Review deliverables | A | R |  |  | R | [6 empty] | R | C | C | C | C
1.7.2 | Final approval | A | C | [5 empty] | C |  |  |  |  | I | I | I | I
2 | Inventory and Compatibility Assessment
2.1 | Gather hardware inventory from all offices | A | R |  | C | C |  |  | C | R |  |  | C | C | C | C | C
2.1.1 | Regional inventory collection | A | R |  | C | C |  |  | C | R |  |  | R | R | R | R | R
2.1.2 | Centralized database update | A | R |  | C | C | R |  | C |  |  |  | C | C | C | C | C
2.2 | Centralized database update | A | C | R | R | R |  |  | C |  |  |  | C | C | C | C | C
2.2.1 | CPU and TPM validation | A | R |  | R |  |  |  | C |  |  |  | C | C | C | C | C
2.2.2 | Memory and disk check | A | R |  | R |  |  |  | C |  |  |  | C | C | C | C | C
2.3 | Identify systems for upgrade vs. replacement | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
2.3.1 | Create replacement list | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
2.3.2 | Identify upgrade-ready systems | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
2.4 | Document compatibility results | A | R |  | C | C |  |  | C |  |  |  | C | C | C | C | C
2.4.1 | Generate reports by region | A | C |  | R | R |  |  | C |  |  |  | R | R | R | R | R
2.4.2 | Submit to management | A | C |  | C | C |  |  | C |  |  |  | I | i | I | I | I
2.5 | Submit assessment report | A | C |  | C | C |  |  | C |  |  |  | I | I | I | I | I
2.5.1 | Compile data | A | C |  | R | R |  |  | C |  |  |  | I | I | I | I | I
2.5.2 | Final review and submission | A | C |  | C | C |  |  | C |  |  |  | I | I | I | I | I
3 | Procurement and Licensing
3.1 | Define hardware specifications | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
3.1.1 | Desktop specs | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
3.1.2 | Laptop specs | A | C |  | R | R |  |  | C |  |  |  | C | C | C | C | C
3.2 | Select and approve vendors | A | C |  | R | R |  | A | C | R |  |  | C | C | C | C | C
3.2.1 | Solicit quotes | A | C |  | R | R |  | R | C |  |  |  | C | C | C | C | C
3.2.2 | Evaluate proposals | A | C |  | R | R |  | R | C |  |  |  | C | C | C | C | C
3.3 | Purchase 1,200 new Windows 11-compatible systems | A | C |  | R | R |  | A | C |  |  |  | C | C | C | C | C
3.3.1 | Issue purchase orders | A | C |  | R | R |  | R | C |  |  |  | C | C | C | C | C
3.3.2 | Confirm delivery schedule | A | C |  | R | R |  | R | C |  |  |  | C | C | C | C | C
3.4 | Acquire Microsoft Volume Licensing | A | C |  | R | R |  |  | C | R |  |  | C | C | C | C | C
3.4.1 | Validate licensing needs | A | C |  | R | R |  |  | C | R |  |  | C | C | C | C | C
3.4.2 | Finalize agreement | A | C |  | R | R |  |  | C | R |  |  | C | C | C | C | C
3.5 | Receive and verify shipments | A | C |  | R | R | R |  | C |  |  |  | C | C | C | C | C
3.5.1 | Inspect hardware | A | C |  | R | R | R |  | C |  |  |  | C | C | C | C | C
3.5.2 | Update asset inventory | A | C |  | R | R | R |  | C |  |  |  | C | C | C | C | C
4 | Deployment Planning
4.1 | Develop deployment strategy and schedule | A | R |  | R | R | [6 empty] | C | C | C | C | C
4.1.1 | Create regional rollout plan | A | R |  | C | R | [6 empty] | R | R | R | R | R
4.1.2 | Align with business priorities | A | R |  | C | R |  |  | C |  |  |  | C | C | C | C | C
4.2 | Assign regional IT leads | A | R | [9 empty] | R | R | R | R | R
4.2.1 | Confirm availability | A | R | [9 empty] | R | R | R | R | R
4.2.2 | Define responsibilities | A | R | [9 empty] | C | C | C | C | C
4.3 | Prepare imaging and configuration tools | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.3.1 | Build standard OS image | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.3.2 | Test configuration settings | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.4 | Set up centralized deployment tools (MECM/WDS) | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.4.1 | Install and configure servers | A | R | C | R | [7 empty] | C | C | C | C | C
4.4.2 | Validate deployment pipeline | A | R |  | R | [7 empty] | C | C | C | C | C
4.5 | Prepare backup and recovery solutions | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.5.1 | Select tools and methods | A | R |  | R | C | [6 empty] | C | C | C | C | C
4.5.2 | Test restore process | A | R |  | R | C | [6 empty] | C | C | C | C | C
TASK ID | TASK DESCRIPTION
5 | System Deployment and Migration
5.1 | Backup user data and profiles | A | R |  | R | [7 empty] | C | R | R | R | R
5.1.1. | Automate backup scripts | A | R |  | R | [7 empty] | C | C | C | C | C
5.1.2 | Store data securely | A | R |  | C | [7 empty] | R | C | C | C | C
5.2 | Deploy Windows 11 on compatible systems | A | R | [9 empty] | C | R | R | R | R
5.2.1 | Schedule upgrade | A | R | [9 empty] | C | R | R | R | R
6.2.2 | Monitor for issues | A | R | [9 empty] | R | C | C | C | C
5.3 | Replace legacy systems with new hardware | A | R |  |  |  | C |  |  | C |  |  | C | R | R | R | R
5.3.1 | Set up new devices | A | R |  |  |  | C | [5 empty] | C | R | R | R | R
5.3.2 | Transfer user roles | A | R | [9 empty] | R | C | C | C | C
5.4 | Restore user data and profiles | A | R | [9 empty] | R | R | R | R | R
5.4.1 | Run restore utility | A | R | [9 empty] | R | R | R | R | R
5.4.2 | Verify user access | A | R | [9 empty] | R | C | C | C | C
5.5 | Verify system functionality and network access | A | R | [9 empty] | R | R | R | R | R
5.5.1 | Test software and connections | A | R | [9 empty] | R | R | R | R | R
5.5.2 | Confirm user satisfaction | A | R | [9 empty] | C | R | R | R | R
6 | User Training and Documentation
6.1 | Develop training materials and user guides | A |  |  | C | R | [5 empty] | R | C | C | C | C | C
6.1.1 | Create multilingual content | A |  |  | C | [6 empty] | R | C | C | C | C | C
6.1.2 | Develop role-based guides | A |  |  | C | R | [5 empty] | R | C | C | C | C | C
6.2 | Schedule training sessions | A | [9 empty] | R | C | C | C | C | C
6.2.1. | Coordinate with departments | A | [9 empty] | R | C | R | R | R | R
6.2.2 | Send invites and materials | A | [9 empty] | R | C | R | R | R | R
6.3 | Deliver live or virtual training sessions | A | [9 empty] | R | C | R | R | R | R
6.3.1 | Conduct instructor-led sessions | A | [9 empty] | R | C | R | R | R | R
6.3.2 | Provide self-paced modules | A | [9 empty] | R | C | C | C | C | C
6.4 | Provide multilingual support (EN, FR, SP, MAN) | A | [9 empty] | R | R | C | C | C | C
6.4.1 | Translate documents | A | [9 empty] | R | C | C | C | C | C
6.4.2 | Staff language-specific support | A | [9 empty] | R | R | C | C | C | C
6.5 | Distribute documentation and FAQs | A | [9 empty] | R | R | C | C | C | C
6.5.1 | Email digital copies | A | [9 empty] | R | R | C | C | C | C
6.5.2 | Upload to company portal | A | [9 empty] | R | R | C | C | C | C
7 | Testing and Support
7.1 | Conduct User Acceptance Testing (UAT) | A |  |  | R | [6 empty] | C | R | C | C | C | C
7.1.1 | Define test cases | A |  |  | R | [7 empty] | R | C | C | C | C
7.1.2 | Collect test results | A |  |  | R | [6 empty] | C | R | C | C | C | C
7.2 | Collect feedback and resolve post-deployment issues | A |  |  | C | [6 empty] | C | R | C | C | C | C
7.2.1 | Open feedback channels | A |  |  | C | [6 empty] | C | R | C | C | C | C
7.2.2 | Track and resolve tickets | A |  |  | C | [7 empty] | R | R | R | R | R
7.3 | Monitor system performance | A |  |  | R | [7 empty] | R | C | C | C | C
7.3.1 | Track KPIs | A |  |  | R | [7 empty] | R | C | C | C | C
7.3.2 | Log incidents | A |  |  | C | [7 empty] | R | C | C | C | C
7.4 | Provide IT helpdesk and on-site support | A | [10 empty] | R | R | R | R | R
7.4.1 | Staff helpdesk | A | [10 empty] | R | C | C | C | C
7.4.2 | Schedule onsite assistance | A | [10 empty] | R | R | R | R | R
7.5 | Final system verification | A |  |  | R | [7 empty] | R | R | R | R | R
7.5.1 | Conduct walkthroughs | A |  |  | R | [7 empty] | R | R | R | R | R
7.5.2 | Confirm readiness with users | A | [10 empty] | R | R | R | R | R
8 | Decommissioning and Recycling
8.1 | Collect and inventory old systems | A |  |  |  |  | R |  |  | C |  |  | C | R | R | R | R
8.1.1 | Tag devices | A |  |  |  |  | R |  |  | C |  |  |  | R | R | R | R
8.1.2 | Record serial numbers | A |  |  |  |  | R | [6 empty] | R | R | R | R
8.2 | Wipe data securely | A |  |  |  |  | R | [5 empty] | R | C | C | C | C
8.2.1 | Use certified tools | A |  |  |  |  | R | [5 empty] | R
8.2.2 | Document data erasure | A |  |  |  |  | R
8.3 | Recycle or dispose of hardware per policy | A |  |  |  |  | R |  |  | R |  |  |  | C | C | C | C
8.3.1 | Work with recycling vendor | A |  |  |  |  | R |  |  | R
8.3.2 | Provide proof of disposal | A |  |  |  |  | R |  |  | R
8.4 | Update asset management records | A |  |  |  |  | R
8.4.1 | Remove decommissioned devices | A |  |  |  |  | R
8.4.2 | Update lifecycle status | A |  |  |  |  | R
9 | Project Closure
9.1 | Final review and evaluation | R | C |  | A | [7 empty] | C
9.1.1 | Conduct performance review | R | C |  | A | [7 empty] | C
9.1.2 | Identify success criteria met | R | C |  | A | [7 empty] | C
9.2 | Obtain sign-off from stakeholders | R | C |  | A
9.2.1 | Schedule final presentation | R | C |  | A
9.2.2 | Get written approval | R | C |  | A
9.3 | Archive documentation and reports | R | C |  | A | [7 empty] | C
9.3.1 | Save project files securely | R |  |  | A | [7 empty] | C
9.3.2' | Notify IT and management | R |  |  | A
9.4 | Conduct lessons learned session | R | C |  | A | [6 empty] | R | C
9.4.1 | Host debrief meeting | R | C |  | A | [6 empty] | R | C
9.4.2 | Compile lessons learned document | R | C |  | A | [6 empty] | R | C
Legend:
R = Responsible (does the work)
A = Accountable (owns the task and makes decisions)
C = Consulted (provides input)
I = Informed (kept up to date)

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.