## WBS Dictionary
WORK BREAKDOWN STRUCTURE DICTIONARY
| PROJECT TITLE | PROJECT ID | COMPANY | PROJECT MANAGER |  |  | Project ID | DATE | VERSION
| Contoso Consulting – Windows 11 Upgrade | CONT-11 | CONTOSO CONSULTING | Sana Rehman¦ sana.rehman@triosstudent.cm |  |  | CONT-11 | April 10th, 20205 | 1.0.0
TASK ID | TASK DESCRIPTION | DEPENDENT UPON | TASK OWNER | TASK RESOURCES | TASK STATUS | ESTIMATED COST | BEGIN DATE | ESTIMATED DATE OF COMPLETION | ACTUAL DATE OF COMPLETION | ADDITIONAL INFO
1 | Project Management
1.1 | Develop project charter |  | Sana | PMO team | 97% | 6000 | 2025-04-07 | 2025-04-09 | 2025-04-09 | Used CloudFunds template
1.1.1 | Define goals and objectives | 1.1 | Sana | Business Analyst | 99% | 1000 | 2025-04-07 | 2025-04-07 | 2025-04-07 | Referenced stakeholder vision
1.1.2 | Identify business drivers | 1.1 | Sana | Project Proposal | 94% | 300 | 2025-04-07 | 2025-04-08 | 2025-04-08 | Based on Windows 11 need
1.2 | Identify stakeholders | 1.1 | Sana | Org Strategy Doc | 98% | 200 | 2025-04-09 | 2025-04-10 | 2025-04-10 | Org-wide identification
1.2.1 | Executive stakeholders | 1.2 | Sana | Org Chart, HR | 99% | 400 | 2025-04-09 | 2025-04-09 | 2025-04-09 | Includes CIO, CTO
1.2.2 | Departmental leads | 1.2 | Sana | Exec Roster | 100% | 150 | 2025-04-10 | 2025-04-10 | 2025-04-10 | Across all departments
1.3 | Define project scope | 1.1 | Sana | HR Records | 100% | 250 | 2025-04-11 | 2025-04-14 | 2025-04-14 | Includes in-scope/out-of-scope
1.3.1 | In-scope items | 1.3 | Sana | Scope Template | 100% | 500 | 2025-04-11 | 2025-04-12 |  | Hardware, training, licenses
1.3.2 | Out-of-scope items | 1.3 | Sana | Requirements Doc | 90% | 200 | 2025-04-12 | 2025-04-14 | 2025-04-14 | Not covered: mobile upgrades
1.4 | Create project schedule | 1.3 | Sana | Planning Notes | 99% | 200 | 2025-04-15 | 2025-04-18 | 2025-04-18 | For Gantt chart
1.4.1 | Define milestones | 1.4 | Sana | MS Project | 99% | 500 | 2025-04-15 | 2025-04-16 | 2025-04-16 | Key deliverabl
1.4.2 | Establish deadlines | 1.4 | Sana | Project Plan | 97% | 300 | 2025-04-16 | 2025-04-17 | 2025-04-18 | Includes buffer
1.5 | Manage project budget | 1.4 | Zain | Project | 100% | 200 | 2025-04-19 | 2025-04-22 | 2025-04-22 | Includes hardware & labor
1.5.1 | Track hardware costs | 1.5 | Zain | Budget Tool | 100% | 1000 | 2025-04-19 | 2025-04-20 | 2025-04-20 | For new PCs &
1.5.2 | Monitor labor costs | 1.5 | Zain | Invoice Records | 99% | 300 | 2025-04-20 | 2025-04-21 | 2025-04-21 | Cross-team hours logged
1.6 | Monitor and report progress | 1.4 | Sana | Timesheets | 75% | 300 | 2025-04-23 | 2025-04-26 |  | weekly updates
1.6.1 | Weekly reports | 1.6 | Sana | PMO Dashboard | 67% | 600 | 2025-04-23 | 2025-04-23 | 2025-04-23 | Status tracking
1.6.2 | Stakeholder updates | 1.6 | Sana | PM Tool | 60% | 300 | 2025-04-24 | 2025-04-25 | 1900-04-08 | Biweekly summary
1.7 | Final sign-off and closeout | 9.2 | Sana | PPT + Email | 0% | 300 | 2025-04-27 | 2025-05-01 |  | Final report + review
1.7.1 | Review deliverables | 1.7 | Sana | Docs, Checklist | 0% | 1000 | 2025-04-27 | 2025-04-28 |  | Based on project scope
1.7.2 | Final approval | 1.7 | Sana | QA Checklist | 0% | 500 | 2025-04-28 | 2025-04-29 |  | Required to close project
2 | Inventory and Compatibility Assessment
2.1 | Gather hardware inventory from all offices | 1.7 | Alia | IT Staff, Inventory Tools | 100% | 500 | 2025-04-07 | 2025-04-10 | 2025-04-10 | Includes coordinating with global offices.
2.1.1 | Regional inventory collection | 2.1 | Alia | Excel, Lansweeper | 100% | 250 | 2025-04-07 | 2025-04-08 | 2025-04-08 | Data gathered per site location.
2.1.2 | Centralized database update | 2.1.1 | Alia | SharePoint, SQL Server | 100% | 150 | 2025-04-08 | 2025-04-09 | 2025-04-09 | All inventory uploaded to central system.
2.2 | Centralized database update | 2.1.2 | CHEN | Microsoft Compatibility Tool | 99% | 400 | 2025-04-09 | 2025-04-11 | 2025-04-09 | Analyzing all system specs against Windows 11 requirements.
2.2.1 | CPU and TPM validation | 2.2 | CHEN | PowerShell Scripts, Microsoft Docs | 60% | 200 | 2025-04-09 | 2025-04-10 | 2025-04-10 | Verifying CPU generation and TPM 2.0 support.
2.2.2 | Memory and disk check | 2.1 | CHEN | Assessment Scripts | 98% | 150 | 2025-04-10 | 2025-04-11 | 2025-04-11 | Ensure minimum 4GB RAM and 64GB storage.
2.3 | Identify systems for upgrade vs. replacement | 2.2.2. | Lisa | Excel, Assessment Data | 99% | 300 | 2025-04-11 | 2025-04-13 | 2025-04-13 | Based on compatibility outcomes.
2.3.1 | Create replacement list | 2.3 | Lisa | Assessment Reports | 99% | 100 | 2025-04-11 | 2025-04-12 | 2025-04-12 | List devices not meeting Windows 11 specs.
2.3.2 | Identify upgrade-ready systems | 2.3.1 | Lisa | Reports, Upgrade Criteria | 99% | 100 | 2025-04-12 | 2025-04-13 | 2025-04-13 | Filter systems that meet minimum requirement
2.4 | Document compatibility results | 2.3.2 | Alia | Microsoft Word, SharePoint | 100% | 150 | 2025-04-13 | 2025-04-13 | 2025-04-14 | Compile compatibility findings into reports.
2.4.1 | Generate reports by region | 2.4 | Alia | Excel, Reporting Template | 0% | 100 | 2025-04-13 | 2025-04-14 | 2025-04-14 | Breakdown of system status by office.
2.4.2 | Submit to management | 2.4.1 | Alia | Email, SharePoint | 97% | 50 | 2025-04-14 | 2025-04-14 | 2025-04-15 | Deliver compatibility reports to upper management.
2.5 | Submit assessment report | 2.4.2 | Alia | Final Report Template | 98% | 100 | 2025-04-14 | 2025-04-15 | 2025-04-15 | Summary report of all findings.
2.5.1 | Compile data | 2.5 | Alia | Inventory Data, Reports | 0% | 50 | 2025-04-14 | 2025-04-15 | 2025-04-15 | Combine inventory, compatibility, and recommendations.
2.5.2 | Final review and submission | 2.5.1 | Sana | Review Checklist | 0% | 50 | 2025-04-15 | 2025-04-15 | 2025-04-15 | Sign-off and formal delivery to stakeholders.
3 | Procurement and Licensing
3.1 | Define hardware specifications | 2.5.2 | Lisa | Hardware Benchmark Reports | 99% | 300 | 2025-04-16 | 2025-04-17 | 2025-04-17 | Use findings from compatibility assessment.
3.1.1 | Desktop specs | 3.1 | Lisa | Windows 11 Hardware Guidelines | 99% | 100 | 2025-04-16 | 2025-04-16 | 2025-04-16 | Define specs for office desktops.
3.1.2 | Laptop specs | 3.1 | Lisa | Market Research, Vendor Catalogs | 99% | 100 | 2025-04-16 | 2025-04-17 | 2025-04-17 | DeProcurement based on RFP process.fine specs for mobile workers
3.2 | Select and approve vendors | 3.1.2 | Fatima | Approved Vendor List | 100% | 250 | 2025-04-17 | 2025-04-19 | 2025-04-19 | Procurement based on RFP process.
3.2.1 | Solicit quotes | 3.2.1.1 | Fatima | Email Templates, RFP Docs | 100% | 100 | 2025-04-17 | 2025-04-18 | 2025-04-18 | Request pricing from vendors.
3.2.2 | Evaluate proposals | 3.2.1.2 | Fatima | Comparison Matrix, Proposal Docs | 90% | 150 | 2025-04-18 | 2025-04-19 | 2025-04-19 | Select vendor based on pricing and warranty.
3.3 | Purchase 1,200 new Windows 11-compatible systems | 3.1.3 | Fatima | Procurement Platform, Vendor Portal | 99% | 900 | 2025-04-20 | 2025-04-22 | 2025-04-22 | Includes desktops and laptops for global office
3.3.1 | Issue purchase orders | 3.3.1.1 | Fatima | Email, Delivery Tracker | 99% | 50 | 2025-04-20 | 2025-04-21 | 2025-04-21 | PO to selected vendor(s).
3.3.2 | Confirm delivery schedule | 3.3.1.2 | Fatima | Manager | 97% | 50 | 2025-04-21 | 2025-04-22 | 2025-04-22 | Coordination across 16 offices.
3.4 | Acquire Microsoft Volume Licensing | 3.1.4 | Amir | Microsoft Licensing Portal | 98% | 1800 | 2025-04-22 | 2025-04-25 | 2025-04-25 | 1200 Windows 11 Pro licenses.
3.4.1 | Validate licensing needs | 3.4.1.1 | Amir | System Count, License Calculator | 98% | 80 | 2025-04-22 | 2025-04-23 | 2025-04-23 | Based on systems and user roles.
3.4.2 | Finalize agreement | 3.4.1.2 | Amir | Microsoft Rep, Legal Review | 100% | 120 | 2025-04-24 | 2025-04-25 | 2025-04-25 | Formal licensing contract.
3.5 | Receive and verify shipments | 3.1.5 | Alia | Shipping Documents | 25% | 200 | 2025-04-24 | 2025-05-01 |  | Multiple phased shipments.
3.5.1 | Inspect hardware | 3.5.1.1 | Alia | Inspection Checklist | 0% | 100 | 2025-04-26 | 2025-04-30 |  | Verify specs and condition.
3.5.2 | Update asset inventory | 3.5.1.2 | Alia | Asset Management Tool | 0% | 100 | 2025-05-01 | 2025-05-01 |  | Log all devices by asset tag and location.
4 | Deployment Planning
4.1 | Develop deployment strategy and schedule | 3.5.2 | Irfan | Prior Project Plans, Office Hours, Business Calendar | 0% | 300 | 2025-05-02 | 2025-05-04 |  | Phased rollout based on region, availability, and critical operatio
4.1.1 | Create regional rollout plan | 4.1 | Irfan | Office Maps, Staffing Charts | 0% | 150 | 2025-05-02 | 2025-05-03 |  | Includes all 16 global offices.
4.1.2 | Align with business priorities | 4.1.1. | Irfan | Executive Input, Business Calendar | 0% | 150 | 2025-05-03 | 2025-05-04 |  | Avoids conflict with peak business periods.
4.2 | Assign regional IT leads | 4.1.2 | Sana | Regional IT Staff Roster | 0% | 200 | 2025-05-05 | 2025-05-06 |  | Assign leads per location
4.2.1 | Confirm availability | 4.2 | Sana | IT Availability Reports | 0% | 100 | 2025-05-05 | 2025-05-05 |  | Confirm readiness and travel, if required.
4.2.2 | Define responsibilities | 4.2.1 | Sana | Deployment Plan, RACI Chart | 0% | 100 | 2025-05-06 | 2025-05-06 |  | Clarify onsite and remote tasks.
4.3 | Prepare imaging and configuration tools | 4.2.2 | Chen | Windows 11 Image, Configuration Toolkit | 0% | 500 | 2025-05-07 | 2025-05-10 |  | Standardized for all models.
4.3.1 | Build standard OS image | 4.3 | Chen | Windows 11 ISO, Configuration Scripts | 0% | 250 | 2025-05-07 | 2025-05-08 |  | Includes company apps and settings.
4.3.2 | Test configuration settings | 4.3.1 | Chen | Test Devices, Checklists | 0% | 250 | 2025-05-09 | 2025-05-10 |  | Validate security and compatibility.
4.4 | Set up centralized deployment tools (MECM/WDS) | 4.3.2 | Chen | MECM, WDS, Network Topology | 0% | 1000 | 2025-05-11 | 2025-05-15 |  | Used for automated deployment
4.4.1 | Install and configure servers | 4.4 | Chen | Virtual Hosts, MECM Setup Files | 0% | 500 | 2025-05-11 | 2025-05-13 |  | Hosted at HQ and major regions.
4.4.2 | Validate deployment pipeline | 4.4.1 | Chen | Test Devices, Log Files | 0% | 500 | 2025-05-14 | 2025-05-15 |  | Used in case of failure during deployment.
4.5 | Prepare backup and recovery solutions | 4.4.2 | Lisa | Backup Tools, Cloud Services | 0% | 700 | 2025-05-16 | 2025-05-18 |  | Test full OS push end-to-end.
4.5.1 | Select tools and methods | 4.5 | Lisa | Backup Catalog, Risk Reports | 0% | 350 | 2025-05-16 | 2025-05-17 |  | Cloud + local hybrid.
4.5.2 | Test restore process | 4.5.1 | Lisa | Test Images, Recovery Protocol | 0% | 350 | 2025-05-17 | 2025-05-18 |  | Ensure fast system recovery.
5 | System Deployment and Migration
5.1 | Backup user data and profiles | 4.3 – Finalize deployment plan | Emma | IT Staff, Backup Software | 70% | 5000 | 2025-04-18 | 2025-04-22 | 2025-04-23 | Focus on critical departments first
5.1.1. | Automate backup scripts | nonw | Emma | Scripting Tools, Endpoint | 100% | 1000 | 2025-04-15 | 2025-04-16 | 2025-04-16 | Scripts use Robocopy and Volume Shadow Copy
5.1.2 | Store data securely | 5.1.1 | Emma | Encrypted Storage, File Servers | 60% | 2000 | 2025-04-17 | 2025-04-19 | 2025-04-19 | Data is encrypted at rest using BitLocker
5.2 | Deploy Windows 11 on compatible systems | 5.1 | Andre | IT Staff, Deployment Tools | 30% | 12000 | 2025-04-23 | 2025-04-30 |  | SCCM/Intune deployment strategy
5.2.1 | Schedule upgrade | 5.2 | Andre | Deployment Calendar, Communication Tools | 100% | 500 | 2025-04-21 | 2025-04-22 | 2025-04-22 | Schedule based on region and priority
6.2.2. | Monitor for issues | 5.2.1 | Andre | Monitoring Tools, Helpdesk | 40% | 1500 | 2025-04-23 | 2025-05-01 |  | Use Endpoint Analytics for feedback
5.3 | Replace legacy systems with new hardware | 5.2 | Mei | Procurement Team, Techs | 0% | 25000 | 2025-05-02 | 2025-05-10 |  | For systems not compatible with Win1
5.3.1 | Set up new devices | 5.3 | Mei | Hardware, Setup Tools | 0% | 10000 | 2025-05-03 | 2025-05-07 |  | Devices pre-imaged with Win11 and apps
5.3.2 | Transfer user roles | 5.3.1 | Mei | AD Admins, Group Policy | 0% | 1000 | 2025-05-08 | 2025-05-09 |  | Includes re-assigning permissions and profiEnsure data maps to correct usersles
5.4 | Restore user data and profiles | 5.2.2 | Mei | Backup Storage, Restore Tools | 0% | 4000 | 2025-05-11 | 2025-05-14 |  | Ensure data maps to correct users
5.4.1 | Run restore utility | 5.4.1 | David | Backup Tools, Access Rights | 0% | 1000 | 2025-05-11 | 2025-05-12 |  | Use same tool as backup for compatibility
5.4.2 | Verify user access | 5.4.1 | David | User Feedback, Testing Tools | 0% | 500 | 2025-05-13 | 2025-05-14 |  | Confirm access to files and apps
5.5 | Verify system functionality and network access | 5.4.2 | Andre | QA Tools, Network Test | 0% | 3000 | 2025-05-15 | 2025-05-18 |  | Final verification before go-live
5.5.1 | Test software and connections | 5.5 | Andre | Test Scripts, Device Access | 0% | 1000 | 2025-05-15 | 2025-05-16 |  | Check all critical business apps
5.5.2 | Confirm user satisfaction | 5.5.1 | Andre | Surveys, Feedback Forms | 0% | 500 | 2025-05-17 | 2025-05-18 |  | Gather feedback via Microsoft Forms
6 | User Training and Documentation
6.1 | Develop training materials and user guides | Project Plan Approved | Ravi | Technical Writer, Translator, SMEs | 98% | 8000 | 2025-04-18 | 2025-04-25 | 2025-04-25 | Includes slide decks and help documents
6.1.1 | Create multilingual content | 6.1 | Ravi | Translator, Editor | 96% | 2500 | 2025-04-19 | 2025-04-23 | 2025-04-23 | EN, FR, SP, MAN
6.1.2 | Develop role-based guides | 6.1 | Ravi | SMEs, QA | 93% | 1800 | 2025-04-18 | 2025-04-24 | 2025-04-24 | Admin, User, IT
6.2 | Schedule training sessions | 6.1.2 | Ravi | Dept. Liaisons | 20% | 500 | 2025-04-25 | 2025-04-27 |  | Internal scheduling tool
6.2.1 | Coordinate with departments | 6.2 | Ravi | Dept. Managers | 30% | 0 | 2025-04-25 | 2025-04-26 |  | Confirm availability
6.2.2 | Send invites and materials | 6.2 | Ravi | Email System | 0% | 0 | 2025-04-26 | 2025-04-27 |  | Use mailing list
6.3 | Deliver live or virtual training sessions | 6.2 | Ravi | Trainers, Zoom/Teams | 0% | 4000 | 2025-04-28 | 2025-05-02 |  | Mix of in-person and virtual
6.3.1 | Conduct instructor-led sessions | 6.3 | Ravi | Presentation Tools | 0% | 2500 | 2025-04-28 | 2025-04-30 |  | 1 per region
6.3.2 | Provide self-paced modules | 6.3 | Ravi | LMS, Multimedia Tools | 0% | 1500 | 2025-04-29 | 2025-05-02 |  | Hosted on intranet
6.4 | Provide multilingual support (EN, FR, SP, MAN) | 6.3.2 | Ravi | Language-Specific Agents | 0% | 3000 | 2025-05-01 | 2025-05-05 |  | EN, FR, SP, MAN
6.4.1 | Translate documents | 6.1.1 | Ravi | Translation Software | 99% | 1000 | 2025-04-20 | 2025-04-23 | 2025-04-23 | Human + AI tools
6.4.2 | Staff language-specific support | 6.4 | Ravi | Bilingual IT Support Staff | 0% | 2000 | 2025-05-01 | 2025-05-05 |  | Contracted support
6.5 | Distribute documentation and FAQs | 6.1 | Ravi | Email, Intranet Admin | 0% | 0 | 2025-05-03 | 2025-05-04 |  | PDF & HTML formats
6.5.1 | Email digital copies | 6.5 | Ravi | Email Tool | 0% | 0 | 2025-05-03 | 2025-05-03 |  | Targeted lists
6.5.2 | Upload to company portal | 6.5 | Ravi | Web CMS | 0% | 0 | 2025-05-03 | 2025-05-04 |  | Secure document storage
7 | Testing and Support
7.1 | Conduct User Acceptance Testing (UAT) | 6.5.2 | Ron | esters, End Users | 0% | 2000 | 2025-05-05 | 2025-05-09 |  | Include power users
7.1.1 | Define test cases | 7.1 | Ron | QA Team | 0% | 500 | 2025-05-05 | 2025-05-06 |  | Align with business needs
7.1.2 | Collect test results | 7.1 | Ron | Testers | 0% | 500 | 2025-05-06 | 2025-05-09 |  | Track in Excel or Jira
7.2 | Collect feedback and resolve post-deployment issues | 7.1.2 | Aisha | Feedback Tools | 0% | 1000 | 2025-05-10 | 2025-05-17 |  | Anonymous & direct feedback
7.2.1 | Open feedback channels | 7.2 | Aisha | Email, Forms | 0% | 200 | 2025-05-10 | 2025-05-11 |  | Email, web forms
7.2.2 | Track and resolve tickets | 7.2 | Aisha | Ticketing System | 0% | 800 | 2025-05-11 | 2025-05-17 |  | SLA of 48 hours
7.3 | Monitor system performance | 7.2.2 | Ron | Monitoring Tools | 0% | 1500 | 2025-05-10 | 2025-05-20 |  | Dashboards, logs
7.3.1 | Track KPIs | 7.3 | Ron | Monitoring Tools | 0% | 700 | 2025-05-10 | 2025-05-15 |  | CPU, uptime, latency
7.3.2 | Log incidents | 7.3 | Ron | Logging System | 0% | 800 | 2025-05-11 | 2025-05-20 |  | Linked to ticketing
7.4 | Provide IT helpdesk and on-site support | 6.3.2 | Aisha | Onsite & Remote IT | 0% | 3000 | 2025-05-01 | 2025-05-20 |  | Local and global support
7.4.1 | Staff helpdesk | 7.4 | Aisha | IT Technicians | 0% | 1000 | 2025-05-01 | 2025-05-04 |  | Tier 1 & Tier 2
7.4.2 | Schedule onsite assistance | 7,4 | Aisha | Field Techs | 0% | 2000 | 2025-05-03 | 2025-05-20 |  | Regional visits
7.5 | Final system verification | 7.3.2 | Aisha | End Users, QA | 0% | 500 | 2025-05-20 | 2025-05-22 |  | Confirm 100% readiness
7.5.1 | Conduct walkthroughs | 7.5 | Aisha | SMEs | 0% | 250 | 2025-05-20 | 2025-05-21 |  | Sample group verification
7.5.2 | Confirm readiness with users | 7.5 | Aisha | User Reps | 0% | 250 | 2025-05-21 | 2025-05-22 |  | Sign-off forms
8 | Decommissioning and Recycling
8.1 | Collect and inventory old systems | Deployment Completed | Zara | IT Technicians, Inventory System | 0% | 1500 | 2025-05-28 | 2025-05-30 |  | Tag and sort devices by site
8.1.1 | Tag devices | 8.1 | Zara | Asset Tags, Scanners | 0% | 500 | 2025-05-28 | 2025-05-29 |  | Barcode or QR
8.1.2 | Record serial numbers | 8.1 | Zara | Asset Management Software | 0% | 300 | 2025-05-29 | 2025-05-30 |  | Cross-check with old inventory
8.2 | Wipe data securely | 8.1.2 | Zara | Data Wipe Software, Audit Team | 0% | 2000 | 2025-05-31 | 2025-06-01 |  | Blancco or DBAN tools
8.2.1 | Use certified tools | 8.2.1.1 | Zara | Data Erasure Tools | 0% | 1200 | 2025-05-31 | 2025-05-31 |  | Compliant with ISO/DoD
8.2.2 | Document data erasure | 8.2 | Zara | Reporting Tool | 0% | 800 | 2025-06-01 | 2025-06-01 |  | Certificate of erasure
8.3 | Recycle or dispose of hardware per policy | 8.2.2 | Zara | Recycling Vendor | 0% | 1800 | 2025-06-02 | 2025-06-04 |  | Green disposal policy
8.3.1 | Work with recycling vendor | 8.3 | Zara | Vendor Liaison | 0% | 1500 | 2025-06-02 | 2025-06-03 |  | Partner preselected
8.3.2 | Provide proof of disposal | 8.3 | Zara | Signed Certificates | 0% | 300 | 2025-06-04 | 2025-06-04 |  | Save PDF copies
8.4 | Update asset management records | 8.3.2 | Alia | Asset System Admin | 0% | 500 | 2025-06-05 | 2025-06-06 |  | Update internal systems
8.4.1 | Remove decommissioned devices | 8.4 | Alia | CMDB Tool | 0% | 350 | 2025-06-05 | 2025-06-05 |  | Flagged as “Retired”
8.4.2 | Update lifecycle status | 8.4 | Alia | Lifecycle Mgmt. Tool | 0% | 250 | 2025-06-06 | 2025-06-06 |  | Ensure compliance logs
9 | Project Closure
9.1 | Final review and evaluation | All project tasks | Sana | PMO Team | 0% | 1000 | 2025-06-03 | 2025-06-04 |  | Summary evaluation report
9.1.1 | Conduct performance review | 9.1 | Sana | Project Reports | 0% | 600 | 2025-06-03 | 2025-06-03 |  | Check against KPIs
9.1.2 | Identify success criteria met | 9.1 | Sana | Metrics Dashboard | 0% | 400 | 2025-06-04 | 2025-06-04 |  | Checklist format
9.2 | Obtain sign-off from stakeholders | 9.1 | Sana | Stakeholders | 0% | 0 | 2025-06-05 | 2025-06-05 |  | Email approval format
9.2.1 | Schedule final presentation | 9.2 | Sana | Meeting Tool | 0% | 0 | 2025-06-05 | 2025-06-05 |  | 1-hour overview
9.2.2 | Get written approval | 9.2 | Sana | Signature Tools | 0% | 0 | 2025-06-05 | 2025-06-05 |  | DocuSign preferred
9.3 | Archive documentation and reports | 9.2.2 | Sana | IT Storage Admin | 0% | 300 | 2025-06-05 | 2025-06-06 |  | Secure access only
9.3.1 | Save project files securely | 9.3 | Sana | SharePoint / Cloud | 0% | 200 | 2025-06-05 | 2025-06-05 |  | Password-protected folders
9.3.2' | Notify IT and management | 9.3 | Sana | Email System | 0% | 100 | 2025-06-06 | 2025-06-06 |  | Include link to archive
9.4 | Conduct lessons learned session | 9.3.2 | Sana | All Team Members | 0% | 500 | 2025-06-06 | 2025-06-06 |  | 1–2 hour team workshop
9.4.1 | Host debrief meeting | 9.4 | Sana | Meeting Tools | 0% | 300 | 2025-06-06 | 2025-06-06 |  | Collect feedback
9.4.2 | Compile lessons learned document | 9.4 | Sana | Word Processor | 0% | 200 | 2025-06-06 | 2025-06-06 |  | Archive with final docs
0%
0%
0%
0%
0%
0%
0%
0%
0%
|  |  |  | ESTIMATED TOTAL |  | 430

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.