| Project Budget |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROJECT TITLE | PROJECT ID | COMPANY | PROJECT MANAGER |  |
| Contoso Consulting – Windows 11 Upgrade | CONT-11 | CONTOSO CONSULTING | Sana Rehman |  |
| TASK ID | TASK DESCRIPTION | Allocated | Contingency Reserve | Total |
| 1.1.1 | Define goals and objectives | $1,000 | $100 | $1,100 |
| 1.1.2 | Identify business drivers | $1,000 | $100 | $1,100 |
| 1.2.1 | Executive stakeholders | $700 | $70 | $770 |
| 1.2.2 | Departmental leads | $800 | $80 | $880 |
| 1.3.1 | In-scope items | $900 | $90 | $990 |
| 1.3.2 | Out-of-scope items | $900 | $90 | $990 |
| 1.4.1 | Define milestones | $1,000 | $100 | $1,100 |
| 1.4.2 | Establish deadlines | $1,000 | $100 | $1,100 |
| 1.5.1 | Track hardware costs | $800 | $80 | $880 |
| 1.5.2 | Monitor labor costs | $800 | $80 | $880 |
| 1.6.1 | Weekly reports | $1,000 | $100 | $1,100 |
| 1.6.2 | Stakeholder updates | $1,000 | $100 | $1,100 |
| 1.7.1 | Review deliverables | $900 | $90 | $990 |
| 1.7.2 | Final approval | $900 | $90 | $990 |
| 2.1.1 | Regional inventory collection | $2,000 | $200 | $2,200 |
| 2.1.2 | Centralized database update | $1,500 | $150 | $1,650 |
| 2.2.1 | CPU and TPM validation | $1,200 | $120 | $1,320 |
| 2.2.2 | Memory and disk check | $1,200 | $120 | $1,320 |
| 2.3.1 | Create replacement list | $1,000 | $100 | $1,100 |
| 2.3.2 | Identify upgrade-ready systems | $1,000 | $100 | $1,100 |
| 2.4.1 | Generate reports by region | $1,500 | $150 | $1,650 |
| 2.4.2 | Submit to management | $1,000 | $100 | $1,100 |
| 2.5.1 | Compile data | $1,000 | $100 | $1,100 |
| 2.5.2 | Final review and submission | $1,000 | $100 | $1,100 |
| 3.1.1 | Desktop specs | $2,000 | $200 | $2,200 |
| 3.1.2 | Laptop specs | $2,000 | $200 | $2,200 |
| 3.2.1 | Solicit quotes | $1,500 | $150 | $1,650 |
| 3.2.2 | Evaluate proposals | $1,500 | $150 | $1,650 |
| 3.3.1 | Issue purchase orders | $1,000 | $100 | $1,100 |
| 3.3.2 | Confirm delivery schedule | $1,000 | $100 | $1,100 |
| 3.4.1 | Validate licensing needs | $1,500 | $150 | $1,650 |
| 3.4.2 | Finalize agreement | $1,500 | $150 | $1,650 |
| 3.5.1 | Inspect hardware | $2,000 | $200 | $2,200 |
| 3.5.2 | Update asset inventory | $2,000 | $200 | $2,200 |
| — | Bulk purchase of 1,200 systems | $960,000 | $96,000 | $1,056,000 |
| — | Microsoft Volume Licensing (Enterprise) | $180,000 | $18,000 | $198,000 |
| 4.1.1 | Create regional rollout plan | $3,000 | $300 | $3,300 |
| 4.1.2 | Align with business priorities | $2,500 | $250 | $2,750 |
| 4.2.1 | Confirm availability of regional IT leads | $1,500 | $150 | $1,650 |
| 4.2.2 | Define responsibilities | $1,500 | $150 | $1,650 |
| 4.3.1 | Build standard OS image | $3,500 | $350 | $3,850 |
| 4.3.2 | Test configuration settings | $3,000 | $300 | $3,300 |
| 4.4.1 | Install and configure servers | $6,000 | $600 | $6,600 |
| 4.4.2 | Validate deployment pipeline | $2,500 | $250 | $2,750 |
| 4.5.1 | Select tools and methods for backup | $2,000 | $200 | $2,200 |
| 4.5.2 | Test restore process | $2,500 | $250 | $2,750 |
| 5.1.1 | Automate backup scripts | $4,000 | $400 | $4,400 |
| 5.1.2 | Store data securely | $3,500 | $350 | $3,850 |
| 5.2.1 | Schedule upgrade | $2,500 | $250 | $2,750 |
| 5.2.2 | Monitor for issues | $2,000 | $200 | $2,200 |
| 5.3.1 | Set up new devices | $8,000 | $800 | $8,800 |
| 5.3.2 | Transfer user roles | $3,500 | $350 | $3,850 |
| 5.4.1 | Run restore utility | $2,000 | $200 | $2,200 |
| 5.4.2 | Verify user access | $1,500 | $150 | $1,650 |
| 5.5.1 | Test software and connections | $2,500 | $250 | $2,750 |
| 5.5.2 | Confirm user satisfaction | $1,800 | $180 | $1,980 |
| 6.1.1 | Create multilingual content | $4,000 | $400 | $4,400 |
| 6.1.2 | Develop role-based guides | $3,000 | $300 | $3,300 |
| 6.2.1 | Coordinate with departments | $1,500 | $150 | $1,650 |
| 6.2.2 | Send invites and materials | $1,000 | $100 | $1,100 |
| 6.3.1 | Conduct instructor-led sessions | $6,000 | $600 | $6,600 |
| 6.3.2 | Provide self-paced modules | $3,500 | $350 | $3,850 |
| 6.4.1 | Translate documents | $2,500 | $250 | $2,750 |
| 6.4.2 | Staff language-specific support | $3,000 | $300 | $3,300 |
| 6.5.1 | Email digital copies | $800 | $80 | $880 |
| 6.5.2 | Upload to company portal | $1,200 | $120 | $1,320 |
| 7.1.1 | Define test cases | $2,000 | $200 | $2,200 |
| 7.1.2 | Collect test results | $2,000 | $200 | $2,200 |
| 7.2.1 | Open feedback channels | $1,200 | $120 | $1,320 |
| 7.2.2 | Track and resolve tickets | $2,800 | $280 | $3,080 |
| 7.3.1 | Track KPIs | $1,500 | $150 | $1,650 |
| 7.3.2 | Log incidents | $1,500 | $150 | $1,650 |
| 7.4.1 | Staff helpdesk | $5,000 | $500 | $5,500 |
| 7.4.2 | Schedule onsite assistance | $3,500 | $350 | $3,850 |
| 7.5.1 | Conduct walkthroughs | $2,000 | $200 | $2,200 |
| 7.5.2 | Confirm readiness with users | $1,800 | $180 | $1,980 |
| 8.1.1 | Tag devices | $1,000 | $100 | $1,100 |
| 8.1.2 | Record serial numbers | $1,200 | $120 | $1,320 |
| 8.2.1 | Use certified tools for data erasure | $3,000 | $300 | $3,300 |
| 8.2.2 | Document data erasure | $1,500 | $150 | $1,650 |
| 8.3.1 | Work with recycling vendor | $2,500 | $250 | $2,750 |
| 8.3.2 | Provide proof of disposal | $1,000 | $100 | $1,100 |
| 8.4.1 | Remove decommissioned devices from records | $1,000 | $100 | $1,100 |
| 8.4.2 | Update lifecycle status of assets | $1,200 | $120 | $1,320 |
| 9.1.1 | Conduct performance review | $1,500 | $150 | $1,650 |
| 9.1.2 | Identify success criteria met | $1,000 | $100 | $1,100 |
| 9.2.1 | Schedule final presentation | $1,200 | $120 | $1,320 |
| 9.2.2 | Get written approval | $800 | $80 | $880 |
| 9.3.1 | Save project files securely | $600 | $60 | $660 |
| 9.3.2 | Notify IT and management | $500 | $50 | $550 |
| 9.4.1 | Host debrief meeting | $1,200 | $120 | $1,320 |
| 9.4.2 | Compile lessons learned document | $1,000 | $100 | $1,100 |
|  |  |  |  | 0 |
|  | Totals | $1,310,400 | $131,040 | $1,441,440 |

Cost Estimation Technique and Explanation:

The cost estimation for the Contoso Windows 11 Upgrade Project was based on a bottom-up estimation method, where each task was broken down into smaller components, and the costs for each component were calculated individually. This ensures that all project activities, from planning and procurement to deployment and decommissioning, are thoroughly accounted for.

For each task, the following factors were considered:

- Labor Costs: Rates for personnel were determined based on the roles involved (e.g., IT staff, procurement officers, regional IT leads) using the company’s standard compensation framework and market averages.

- Hardware and Software Procurement: Costs were based on vendor quotes and historical prices from similar projects.

- Contingency Reserves: A 10% contingency reserve was applied to each task to account for potential cost fluctuations due to unforeseen circumstances.

For tasks involving hardware procurement and licensing, vendor quotes were used to estimate costs, and for labor, estimated hours were multiplied by the respective hourly rates.

Consideration of Project Resource Rates and Cost Estimate:

- Personnel Costs: Hourly rates for roles like IT Analysts and IT Managers were considered based on the tasks assigned to them, e.g., OS image configuration for an IT Analyst at $100 per hour and strategic oversight for an IT Manager at $150 per hour.

- Vendor and Hardware Rates: Hardware purchases, such as the bulk purchase of 1,200 systems, were estimated using recent quotes from vendors like Dell and Lenovo. Microsoft Volume Licensing was based on quotes from the Microsoft licensing portal.

This methodology ensures an accurate and thorough cost estimate, accounting for all potential costs and the necessary contingency to cover unforeseen changes.