## WBS Dictionary
Communications Plan
| PROJECT TITLE | PROJECT ID | COMPANY | PROJECT MANAGER
| Contoso Consulting – Windows 11 Upgrade | CONT-11 | CONTOSO CONSLUTING | Sana Rehman
Title | Stakeholders | Deliverable | Owner | Frequency | Method | Sing-off
Project Kickoff Meeting | All Stakeholders | Introduce the project, scope, objectives, and team roles. | Sana Rehman | Once (Project Start) | Video Conference (MS Teams) | Sana
Weekly Progress Reports | Project Team & Stakeholders | Provide status updates, key achievements, and blockers. | Sana Rehman | Weekly (Mondays) | Email & SharePoint Upload | Sana
Executive Briefings | Executive Leadership | High-level updates on budget, milestones, and risks. | Sana Rehman | Bi-weekly | Executive Summary Email | Sana,
Team Stand-ups | Project Team | Daily task sync and coordination. | Sana Rehman | Daily (Weekdays) | MS Teams / In-Person | Sana
Issue Escalation Alerts | IT Manager, Project Manager | Immediate notification of critical issues. | Irfan Khan | As Needed | Email / Phone / Teams Alert | Sana | , Irfan
Training Announcements | All End-Users | Notify users of training sessions and materials. | Ravi Patel | As Scheduled | Email / Portal Notification | Ravi
Regional Deployment Notices | Regional IT Teams & Users | Inform about deployment schedules and system downtime. | Emma, Andre, Mei, David | One Week Before Deploy | Email / Local Intranet | Emma, Andre, Mei, David
Post-Deployment Feedback Request | End-Users | Gather user feedback and satisfaction post-upgrade. | Aisha Bello | Within 1 Week Post | Survey via Microsoft Forms | Aisha
Project Milestone Updates | All Stakeholders | Share completion of major milestones (e.g. procurement). | Sana Rehman | Milestone-Based | Email / SharePoint Timeline | Sana
Lessons Learned Session Invite | Project Team & Key Stakeholders | Reflect on project outcomes and improvements. | Sana Rehman | End of Project | Calendar Invite + Video Call | Sana

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.